## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | As a user, I want to register with email and password so that I can access the system. | MUST | Auth Module | Developer 1 | Completed
Sprint 1 | Sprint 1 | US-002 | As a user, I want to log in securely using JWT so that my account is protected. | MUST | US-001 | Developer 1 | Completed
Sprint 1 | Sprint 1 | US-003 | As a user, I want to reset password via OTP to regain access if forgotten. | MUST | SMTP Integration | Developer 1 | Completed
Sprint 1 | Sprint 1 | US-004 | As an Admin, I want to assign user roles (Admin, Staff, Customer) to control access. | MUST | US-001 | Developer 1 | Completed
Sprint 2 | Sprint 2 | US-005 | As Admin, I want to create/edit/delete categories so products are grouped. | MUST | DB Setup | Developer 2 | Completed
Sprint 2 | Sprint 2 | US-006 | As Admin, I want unique category validation so duplicates are prevented. | MUST | US-005 | Developer 2 | Completed
Sprint 2 | Sprint 2 | US-007 | As Admin, I want to add products with details (SKU, stock, brand, price). | MUST | US-005 | Developer 2 | Completed
Sprint 2 | Sprint 2 | US-008 | As Admin, I want to upload product images from my PC. | MUST | File Storage | Developer 2 | Completed
Sprint 3 | Sprint 3 | US-009 | As Admin, I want to add a product image using a public URL. | SHOULD | US-008 | Developer 2 | Completed
Sprint 3 | Sprint 3 | US-010 | As a user, I want to search and filter products by category/price/name. | MUST | US-007 | Developer 3 | Completed
Sprint 3 | Sprint 3 | US-011 | As a Customer, I want to view detailed product info with rating & images. | MUST | US-007 | Developer 3 | Completed
Sprint 3 | Sprint 3 | US-012 | As a Customer, I want to add products to cart with quantity control. | MUST | US-011 | Developer 3 | Completed
Sprint 3 | Sprint 3 | US-013 | As a Customer, I want to save products to wishlist for future purchase. | SHOULD | US-011 | Developer 3 | Completed
Sprint 4 | Sprint 4 | US-014 | As a Customer, I want to checkout securely to place an order. | MUST | US-012 | Developer 3 | Completed
Sprint 4 | Sprint 4 | US-015 | As a Customer, I want to cancel order before shipped to avoid wrong delivery. | MUST | Order Module | Developer 3 | Completed
Sprint 4 | Sprint 4 | US-016 | As Staff, I want to view and update order status for faster processing. | MUST | US-014 | Developer 4 | Completed
Sprint 4 | Sprint 4 | US-017 | As Admin/Staff, I want stock to auto-update after checkout or cancellation. | MUST | US-014 | Developer 4 | Completed
Sprint 5 | Sprint 5 | US-018 | As Customer, I want to give rating & review only after product purchase. | SHOULD | Order History | Developer 5 | Completed
Sprint 5 | Sprint 5 | US-019 | As Admin, I want low-stock alerts via email only so inventory never runs out. | MUST | Inventory Module | Developer 4 | Completed
Sprint 5 | Sprint 5 | US-020 | As Admin, I want sales, stock, and revenue analytics on dashboard. | MUST | Orders Module | Developer 1 | Completed
Sprint 5 | Sprint 6 | US-021 | As Admin/Staff, I want exports to PDF & Excel for business reporting. | SHOULD | US-020 | Developer 6 | In Progress
Sprint 6 | Sprint 6 | US-022 | As a user, I want to update my profile information. | SHOULD | Auth | Developer 6 | Completed
Sprint 6 | Sprint 6 | US-023 | As a user, I want to change my password after login. | SHOULD | US-022 | Developer 6 | Completed
Sprint 6 | Sprint 6 | US-024 | As a user, I want dark/light mode switch in settings UI. | COULD | UI Update | Developer 6 | Completed
Sprint 6 | Sprint 6 | US-025 | As Admin, I want an audit log for major actions (product/role change). | COULD | System Logging | Developer 2 | Backlog
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7