## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Tester | 2025-11-01 | Typo in login error message | Sprint 2 | Developer | UI Defect | Corrected spelling | 2025-11-01 | Closed | Verified
2 | Tester | 2025-11-01 | Button alignment issue on registration page | Sprint 2 | Developer | UI Layout | CSS updated | 2025-11-02 | Closed | UI stable
3 | Tester | 2025-11-02 | Product image stretched on mobile | Sprint 2 | Developer | UI Responsiveness | Fixed aspect ratio | 2025-11-02 | Closed | Passed
4 | Tester | 2025-11-03 | Wishlist icon tooltip missing | Sprint 2 | Developer | UI Minor | Tooltip added | 2025-11-03 | Closed | Verified
5 | Tester | 2025-11-03 | Incorrect currency format in cart | Sprint 3 | Developer | Functional | Price formatter applied | 2025-11-04 | Closed | Correct
6 | Tester | 2025-11-04 | Missing loader during checkout | Sprint 3 | Developer | UX | Loader animation added | 2025-11-04 | Closed | Good
7 | Tester | 2025-11-05 | Stock alert text overlapping icon | Sprint 3 | Developer | UI | Padding adjusted | 2025-11-05 | Closed | Verified
8 | Tester | 2025-11-05 | Focus highlight missing on form fields | Sprint 3 | Developer | Accessibility | Focus style added | 2025-11-06 | Closed | Accessible
9 | Tester | 2025-11-06 | Dashboard card animation delay too long | Sprint 3 | Developer | UX | Duration optimized | 2025-11-06 | Closed | Smooth
10 | Tester | 2025-11-06 | Profile avatar not centered | Sprint 3 | Developer | UI | Alignment fixed | 2025-11-07 | Closed | Passed
11 | Tester | 2025-11-07 | Product card spacing inconsistent | Sprint 4 | Developer | UI Style | Margins standardized | 2025-11-07 | Closed | OK
12 | Tester | 2025-11-08 | Toast fade-out too fast | Sprint 4 | Developer | UX | Increased duration | 2025-11-08 | Closed | Approved
13 | Tester | 2025-11-08 | Cart icon badge clipped on mobile | Sprint 4 | Developer | UI Responsive | Position updated | 2025-11-09 | Closed | Passed
14 | Tester | 2025-11-09 | Login email not auto-focused | Sprint 4 | Developer | UX | Autofocus added | 2025-11-09 | Closed | Verified
15 | Tester | 2025-11-09 | Notification icon refresh delay | Sprint 4 | Developer | Performance | State sync optimized | 2025-11-10 | Closed | Good
16 | Tester | 2025-11-10 | Low stock label wrong color | Sprint 5 | Developer | UI | Theme updated | 2025-11-10 | Closed | Verified
17 | Tester | 2025-11-11 | Review scrollbar abrupt | Sprint 5 | Developer | UI Minor | Smooth scroll enabled | 2025-11-11 | Closed | Retested
18 | Tester | 2025-11-11 | Missing page title in Wishlist | Sprint 5 | Developer | UI | Title added | 2025-11-11 | Closed | Passed
19 | Tester | 2025-11-12 | Enter key not submitting login | Sprint 5 | Developer | Functional | Keyboard handler added | 2025-11-12 | Closed | Verified
20 | Tester | 2025-11-12 | Dark mode toggle abrupt | Sprint 5 | Developer | UX | Smooth transition added | 2025-11-13 | Closed | Better UX
21 | Tester | 2025-11-13 | Search input lacks placeholder | Sprint 5 | Developer | UI | Placeholder text added | 2025-11-13 | Closed | Fixed
22 | Tester | 2025-11-13 | Hover effect too strong | Sprint 5 | Developer | UI | Subtle shadow applied | 2025-11-14 | Closed | Polished
23 | Tester | 2025-11-14 | Minor flicker changing product image | Sprint 6 | Developer | UI/Performance | Added transition | 2025-11-14 | Closed | Good
24 | Tester | 2025-11-14 | Notification timestamp not localized | Sprint 6 | Developer | Format | Local time applied | 2025-11-15 | Closed | Verified
25 | Tester | 2025-11-15 | Add review button too small | Sprint 6 | Developer | UI | Button size increased | 2025-11-15 | Closed | Retested
26 | Tester | 2025-11-15 | Default avatar bad shape | Sprint 6 | Developer | UI | Rounded border applied | 2025-11-16 | Closed | Good
27 | Tester | 2025-11-16 | Rating stars not accessible | Sprint 6 | Developer | Accessibility | ARIA roles added | 2025-11-16 | Closed | Accessible
28 | Tester | 2025-11-16 | Search suggestions clipped UI | Sprint 6 | Developer | UI Responsive | Width adjusted | 2025-11-17 | Closed | Verified
29 | Tester | 2025-11-17 | Success toast lacks icon | Sprint 7 | Developer | UX | Icon added | 2025-11-17 | Closed | Passed
30 | Tester | 2025-11-17 | Category dropdown narrow | Sprint 7 | Developer | UI | Width increased | 2025-11-18 | Closed | Verified
31 | Tester | 2025-11-18 | Cart recalculation slow | Sprint 7 | Developer | Performance | Logic optimized | 2025-11-18 | Closed | Faster
32 | Tester | 2025-11-18 | Tooltip overlapped header | Sprint 7 | Developer | UI | z-index adjusted | 2025-11-19 | Closed | Fixed
33 | Tester | 2025-11-19 | Filters missing shadow | Sprint 7 | Developer | UI Style | Shadow added | 2025-11-19 | Closed | OK
34 | Tester | 2025-11-19 | Placeholder image blurry | Sprint 7 | Developer | Asset Quality | HD image used | 2025-11-20 | Closed | Improved
35 | Tester | 2025-11-20 | Banner animation too fast | Sprint 8 | Developer | UI Animation | Slowed easing | 2025-11-20 | Closed | Smooth
36 | Tester | 2025-11-20 | Round-off mismatch totals | Sprint 8 | Developer | Data Validation | Unified decimal rules | 2025-11-21 | Closed | Confirmed
37 | Tester | 2025-11-21 | Forgot password link faint | Sprint 8 | Developer | UX | Enhanced visibility | 2025-11-21 | Closed | Verified
38 | Tester | 2025-11-21 | Page jump after filtering | Sprint 8 | Developer | UI | Smooth scroll added | 2025-11-22 | Closed | Passed
39 | Tester | 2025-11-22 | Coupon tooltip overlap | Sprint 8 | Developer | UI Minor | Space adjusted | 2025-11-22 | Closed | Verified
40 | Tester | 2025-11-22 | Hover jitter buttons | Sprint 8 | Developer | UI/UX | Animation tuned | 2025-11-23 | Closed | Smooth
41 | Tester | 2025-11-23 | Notification bell no vibration | Sprint 8 | Developer | UX Enhancement | Vibration added | 2025-11-23 | Closed | Works
42 | Tester | 2025-11-24 | Invoice logo misaligned | Sprint 9 | Developer | PDF Layout | Margin corrected | 2025-11-24 | Closed | Perfect
43 | Tester | 2025-11-24 | Success message dull | Sprint 9 | Developer | UI Theme | Brightened background | 2025-11-24 | Closed | Better contrast
44 | Tester | 2025-11-25 | Cart badge not resetting after logout | Sprint 9 | Developer | Functional | State reset added | 2025-11-25 | Closed | Verified
45 | Tester | 2025-11-25 | Edit button misaligned | Sprint 9 | Developer | UI | Text alignment fixed | 2025-11-25 | Closed | OK
46 | Tester | 2025-11-26 | Divider missing in order list | Sprint 9 | Developer | UI Minor | Line added | 2025-11-26 | Closed | Checked
47 | Tester | 2025-11-26 | Coupon code not uppercase | Sprint 9 | Developer | Functional | Auto-format set | 2025-11-26 | Closed | Verified
48 | Tester | 2025-11-27 | Rating filter size mismatch | Sprint 10 | Developer | UI Style | Sizes standardized | 2025-11-27 | Closed | Good
49 | Tester | 2025-11-27 | Pagination icon off-center | Sprint 10 | Developer | UI/Layout | Fixed alignment | 2025-11-27 | Closed | Passed
50 | Tester | 2025-11-28 | Notification unread indicator too small | Sprint 10 | Developer | UX/UI | Dot size increased | 2025-11-28 | Closed | Approved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others